## 2025 Projects
| Project Number | Contract Number | Project Name | Estimate Amount | Bid Estimate | Bid | Planned Advertised Date | Actual Advertised Date | Bid Opening | Comments
Arterial Projects
1 |  |  | Harvard - 31st to 41st | [6 empty] | Delay until summer 2026 - $1.25 Million - Waiting on Lewis 41st to 51st to be completed
2 |  |  | S 193rd E Ave - 11th to 31st | 1500000
3 |  |  | Elwood - 61st to 71st | 1000000
4 |  |  | Lewis - 1st to 10th | 1100000
5 |  |  | 41st - 108th E Ave to 101st St | 2000000
6 | MS 25-001 |  | Arterial Microseal | 1000000 | 1152000 |  |  | 2025-02-14 | 2025-03-14
7
8
9
10
11
12
Non-Arterial Projects
13 | 2024 MPO C7 |  | MZ 5024 Yale to Sheridan / 15th to 21st | 1500000 | 1575000
14 |  |  | MZ 4023 15th & Harvard (NEC) | 700000
15 |  |  | S 92nd E Ave - 71st to 73rd / to Memorial | 1750000
16 | 2025 MPO C1 |  | Mohawk / Winston Ave | 600000 | 875000 |  |  | 2025-02-21 | 2025-03-21
17 |  |  | Ute / Trenton | 1100000
18 | CSM 25-001 |  | 36th & Harvard - Concrete Patching | 1000000 | 750000 |  |  | 2025-02-14 | 2025-03-14
19 |  |  | W 46th St & Union | 1000000
20 |  |  | 109th & Yale | 1200000
21 | MS 25-002 |  | Non-Arterial Microseal | 1000000 | 1100000 |  |  | 2025-02-14 | 2025-03-14
22
23
24
|  |  | Total Arterial Projects to Advertise | 6600000
|  |  | Total Non-Arterial Projects to Advertise | 9850000
|  |  | Total Street Maintenance Projects to Advertise | 16450000